## Bill of Materials -BOM
Content Type | Hybrid Cloud Foundation (by SKO) | Auto-Renewed Certs (by SKO) | Trusted Identity (Post SKO) | Centralized K8s Secrets (Post SKO)
Core Value Pitch / POV (internal alignment doc) | Published | Published | Not-Started | Not-Started
Tactical One Pager | In-Review | In-Review | Not-Started | Not-Started
Discovery Guide | In-Review | In-Review | Not-Started | Not-Started
Objection Handling Guide | In-Review | In-Review | Not-Started | Not-Started
2nd Call Deck | In-Review | In-Review | Not-Started | Not-Started
Demo Video | Not-Started | Not-Started | Not-Started | Not-Started
Demo on DDR | In-Review | In-Review | Not-Started | Not-Started
Workshop | In-Review | In-Progress | Not-Started | Not-Started
Validated Pattern | Not Applicable | In-Progress | Not-Started | Not-Started

## BOM Definitions
Content Type | Purpose
Core Value Pitch / POV | Internal alignment document used to orient group on content creation (will not be published to the field).
Tactical One Pager | Provide an overview for the Account team.
Discovery Guide | Key questions to get more details from the customer so that an Account Team can customize the play. These will be covered during the "1st call" but will also continue to be used to continue gathering information for the duration of the play.
Objection Handling Guide | How do we respond and address customer questions / concerns in order to move the play forward.
2nd Call Deck | Deck used by the Account Team to explain the challenges and our proposed solution. A significant portion of this will be Technical but will also cover the business value.
Demo Video | A video of the demo - the demo could be provided by the SE during the 2nd call presentation and or in a further step after that.
Demo on DDR | A standard / prescriptive demo, developed by SE community and maintained by the CDL team that will be hosted on the DDR platform. This will allow an SE to do a demo with minimum bespoke work.
Workshop | We expect to use existing Workshop materials unless gaps are identified. This refers primarily to the development of a "packaging deck" which will orient the customer and describe the problems being solved / outcomes realised. Refer to Field Marketing Workshop decks as examples of what is required.
Validated Pattern | Detailed guidance on how the technical solution will be implemented by the customer. This will be our official guidance and will be used by PS, SA community as well to ensure that the customer is getting a single opionated view.

## Content RACI
Work In Progress
Content Type | VE Interlock | VE Strategist | CDL | Product Marketing | R&D | SE Org | TAM Org | FCTO Org | SA Org | PS Org
Core Value Pitch / POV | Responsible | Accountable | Informed | Consulted | Informed | Responsible | Informed | Consulted | Consulted | Informed
Discovery Questions | Accountable | Responsible | Informed | Consulted | Informed | Responsible | Informed | Consulted | Consulted | Informed
Objection Handling | Accountable | Responsible | Informed | Consulted | Informed | Responsible | Informed | Consulted | Consulted | Informed
2nd Call Deck | Accountable | Responsible | Informed | Consulted | Consulted | Responsible | Consulted | Consulted | Consulted | Informed
Demo Video | Accountable | Accountable | Responsible | Consulted | Informed | Responsible | Informed | Informed | Consulted | Informed
Demo on DDR | Accountable | Accountable | Responsible | Consulted | Informed | Responsible | Consulted | Informed | Consulted | Informed
Workshop | Accountable | Accountable | Responsible | Consulted | Informed | Responsible | Informed | Informed | Consulted | Informed
Validated Pattern | Accountable | Accountable | Informed | Consulted | Consulted | Consulted | Consulted | Informed | Responsible | Informed

## Working Group
| HC Role | Working Group Role | Which Play | Location (call scheduling) | Comments
Joani Delaporte | Sr SA | Consulted / Build | Any + RedHat | US
Chris Zembower | Sr Staff RSA | Consulted / Build | Any + RedHat | US | see below for Certs
Ben Holmes | Staff SE | Consulted / Build | Any + RedHat | UK
Gerald Dykeman | Staff SE | Consulted / Build | Any + RedHat | US
Rob Fitton | CLM Leadership | Consulted / Informed | All
Erik Rygg | SA Leadership | Consulted / Informed | All
Moayad Ismail | SA Leadership | Consulted / Informed | All
Corrigan Neralich | SE Leadership | Consulted / Informed | All
Tony Pulickal | SE Leadership | Consulted / Informed | All
John DaDamio | SE Leadership | Consulted / Informed | All
Vishwas Krishnaswamy | VE Leadership (CDL) | Consulted / Informed | All for Workshops and Demos
Bryan Sadowski | VE Leadership (VP) | Consulted / Informed | All
Kyle Ruddy | TPMM | Consulted | All
Cailin Kearns | Enablement | Enablement | All
Kazi Rahman | Enablement | Enablement | All
Michelle Roberts | VE Leadership (Programs) | Overall Program Execution Strategy | All
Michael Wood | VE Leadership (Strategist) & FCTO | Overall Program Vision | All
Adam Cavaliere | VE Leadership (Interlock) | Overall Program Vision | All
Fiona Black | VE TPM | Program Management of BOM items, stitching with SKO session | All
Ian Kemp | VE TPM | Program Management of Demos, Workshops | All
Amber Reddy | VE TPM | Program Management of Validated Patterns | All
Adeel Ahmad | Strategist | Macro Strategy & Cohesiveness across plays | Macro Level | UK
Troy Fluegge | Interlock | Vision & Build | Auto Renewed Certs | US
Prakash Manglanathan | Interlock | Vision & Build | Cloud Foundations | US
Geoff Korrub | Strategist | Vision & Build | Auto Renewed Certs | US
Mike Wright | Strategist | Vision & Build | Cloud Foundations | US
Nico Kabar | Sr Staff SE | Build | Auto Renewed Certs | US
Yulei Liu | Sr Staff SE | Build | Auto Renewed Certs | Australia | timezone diff, too difficult to engage
Cooper Melgreen | Staff SE | Build | Auto Renewed Certs | US
David Howes | Staff SE | Build | Auto Renewed Certs | US
Justin DeFrank | Staff SE | Build | Auto Renewed Certs | US
Mike Fonseca | Staff SE | Build | Cloud Foundations | US
Ricardo Oliveira | Staff SE | Reviewer | Cloud Foundations | UK | No bandwidth. Reviewer only
Miles Harrison | Staff SE | Build | Cloud Foundations | US
Omid Eghaneyan | Staff SE | Build | Cloud Foundations | US
Simon Lynch | SA | Validated Pattern | Cloud Foundations | Australia | timezone diff, too difficult to engage
Kaitlyn Davis | SA | Validated Pattern | Cloud Foundations | US
Shyam Chaganti | SA | Validated Pattern | Cloud Foundations | US
Kranthi Katepalli | SA | Review if needed |  | US | Remove, use as reviewer as needed
Nick Wales | SA | Review if needed |  | US | no answer
Vijay Sharma | SA | Review if needed |  | US | Remove, use as reviewer as needed
Andrew Thielen | SA | Validated Pattern | Auto Renewed Certs | US
Jan Repnak | SA | Validated Pattern | Auto Renewed Certs | UK
Chris Zembower | Sr Staff RSA | Consulted / Build | Auto Renewed Certs | US | Also above for +Red Hat
Guilherme Pamplona Santos | Sr SE | Build | Auto Renewed Certs | US
Paul Nosevich | Sr SE | Build | Auto Renewed Certs | US | out sick, did not contribute
Rama Chavali | SE 3 | Build | Auto Renewed Certs | US
Mahil El Khatib | Sr SE | Build | Auto Renewed Certs | EMEA | was out sick, limited reviewer
Dave Randolph | Sr SE | Build | Cloud Foundations | US
Nivetha Narayanan | Corporate SE | Review | All | US / Joe Levingston
George Doykan | Corporate SE | Review | All | US / Joe Levingston
Sonya Pieklik | Corporate SE | Review | All | US / Joe Levingston
Jacob Buckles | Corporate SE | Review | All | US / Joe Levingston
Patricia Rojas | Corporate SE | Review | All | US / Joe Levingston
Tim Olson | Staff SE | Review | All | US / Tim Silk
Andy Baran | CSE | Review | All
Greg LoRang | CSE | Review | All

## Source of Truth
BOM Category | Play | JIRA Ticket | Task Detail | Start Date | End Date | LOE Business Days | Build Resource | Status | Health | Notes
Enablement | SKO Session |  | SKO Session Build | 2025-01-06 | 2025-01-31 | 28 |  | Development | On Track
Enablement | SKO Session |  | Refine and Prep | 2025-02-03 | 2025-02-14 | 10 |  | Development | On Track
SKO | Key Milestone |  | SKO | 2025-02-17 | 2025-02-21 | 5 |  | Not Started | Not Started
Point of View: Problem Statement and Value Solved | Cloud Foundations |  | Problem Statement and Value Solved (Point of View Drafted) | 2025-01-07 | 2025-01-10 | 4 | Prakash Manglanathan Mike Wright | Published | Published
Point of View: Problem Statement and Value Solved | Cloud Foundations |  | Problem Statement and Value Solved (Alignment) | 2025-01-13 | 2025-01-13 | 1 | All | Published | Published
Sales One Pager | Cloud Foundations |  | Sales One Pager (Build) | 2025-01-14 | 2025-02-07 | 3 | Prakash Manglanathan Mike Wright | Development | Under Review | Feedback underway
Handoff | Cloud Foundations |  | Handoff Sales One Pager to All Downstream | 2025-01-24 | 2025-01-24 | 1 | Fiona Black | Development | On Track | Working in parallel
Validated Pattern | Cloud Foundations |  | Validated Pattern (Build) |  |  | 0 |  | Will not do | Not Started | Tactical Play does not require a Validated Pattern as per discussion with Dan Brown Prakash and I discussed HVD vs HVP and we agreed that this tactical play topic is better suited to HVD as this is something every Terraform user should be doing. This seems like a good line to determine if something should be elevated from an HVP to an HVD. I think patterns should be followed if you want to do something with Terraform, whereas designs should be followed as part of every user journey.
2nd Call Deck | Cloud Foundations |  | 2nd Call Deck (Build) | 2025-01-17 | 2025-02-07 | 5 | Mike Fonseca Dave Randolph | Development | Under Review | Feedback underway
Handoff | Cloud Foundations |  | Handoff 2nd Call Deck to CDL (Workshop) | 2025-01-24 | 2025-01-24 | 1 | Amber Reddy, Fiona Black | Development | On Track | Working in parallel
CDL - Workshop | Cloud Foundations |  | Workshop Slides and Assembly (Build) | 2025-01-17 | 2025-02-07 | 5 | Miles Harrison Shyam Chaganti | Development | Under Review | Feedback underway
CDL - Demo | Cloud Foundations |  | Demo (Build) | 2025-01-17 | 2025-02-11 | 5 | Omid Eghaneyan Kaitlyn Davis | Development | Under Review | Readme being finalised, Demo requires further SE review and feedback post SKO
CDL - Demo Recording | Cloud Foundations |  | Demo recording for 2nd call Deck | 2025-02-24 | 2025-02-28 | 1 |  | Not Started | Not Started | Is this just a bite size demo to whet the appetite for the full DDR Demo?
CDL - Demo Context Slides | Cloud Foundations |  | Customer Facing Context Slides | 2025-02-24 | 2025-02-28 | 1 |  | Not Started | Not Started | Context slides to oriente the customer if the Demo is used on its own/not show within the context of the 2nd call deck
Discovery Guide | Cloud Foundations |  | Discovery Guide (Build) | 2025-01-17 | 2025-02-07 | 5 | Adeel Ahmad Mike Wright | Development | Under Review | Feedback underway
Objection Handling Guide | Cloud Foundations |  | Objection Handing Guide (Build) | 2025-01-17 | 2025-02-07 | 5 | Adeel Ahmad Mike Wright | Development | Under Review | Feedback underway
Handoff | Cloud Foundations |  | Handoff for publishing (Highspot / Playbooks) | 2025-03-07 | 2025-03-07 | 1 | Fiona Black | Not Started | Not Started | Design needed / Post SKO
Feedback | Cloud Foundations |  | TFO, BVS, Sales feedback | 2025-02-24 | 2025-03-05 | 3 |  | Not Started | Not Started
Design Work | Cloud Foundations |  | Content to Creative Design for polishing | 2025-03-10 | 2025-03-14 | 5 | Fiona Black | Not Started | Not Started
Publish | Cloud Foundations |  | Publish (Prep) | 2025-03-17 | 2025-03-18 | 2 | Cailin Kearns Claudia Lannes | Not Started | Not Started
Publish | Cloud Foundations |  | Publish (Highspot) | 2025-03-18 | 2025-03-18 | 1 | Cailin Kearns | Not Started | Not Started
Publish | Cloud Foundations |  | Publish (Playbooks) | 2025-03-18 | 2025-03-21 | 3 | Claudia Lannes | Not Started | Not Started
Point of View: Problem Statement and Value Solved | Auto Renewed Certs |  | Problem Statement and Value Solved (Point of View Drafted) | 2025-01-07 | 2025-01-10 | 4 | Troy Fluegge Geoff Korrub | Published | Published
Point of View: Problem Statement and Value Solved | Auto Renewed Certs |  | Problem Statement and Value Solved (Alignment) | 2025-01-13 | 2025-01-24 | 1 | All | Published | Published
Sales One Pager | Auto Renewed Certs |  | Sales One Pager (Build) | 2025-01-14 | 2025-02-07 | 3 | Justin DeFrank | Development | Under Review
Handoff | Auto Renewed Certs |  | Handoff Sales One Pager to All Downstream | 2025-01-16 | 2025-01-16 | 1 | Fiona Black | Development | On Track | working in parallel
Validated Pattern | Auto Renewed Certs | https://hashicorp.atlassian.net/browse/HVD-1729 | Validated Pattern (Build) : Vault PKI with Vault Agent | 2025-01-24 | 2025-02-28 | 7 | Jan RepnakChris Zembower Andrew Thielen | Development | On Track | Plan done, tickets created, WIP. Publishing post SKO.
Validated Pattern | Auto Renewed Certs |  | Validated Pattern (Build) : Additional Consumption Patterns |  |  | 7 |  | Not Started | Not Started | To be scoped, planned and resourced when the first VP is completed
2nd Call Deck | Auto Renewed Certs |  | 2nd Call Deck (Build) | 2025-01-17 | 2025-02-14 | 5 | Cooper Melgreen Rich DuBose | Development | On Track | further Enterprise features being incorporated
Handoff | Auto Renewed Certs |  | Handoff Validated Pattern & 2nd Call Deck to CDL (Workshop) | 2025-01-24 | 2025-01-24 | 1 | Amber Reddy, Fiona Black | Development | On Track | working in parallel
CDL - Workshop | Auto Renewed Certs |  | Workshop Slides and Assembly (Build) | 2025-01-27 | 2025-02-10 | 5 | Rama Chavali | Development | On Track | Working group call, feedback provided. Track update will be done by CDL post SKO
CDL - Workshop | Auto Renewed Certs | https://hashicorp.atlassian.net/browse/VCDL-2028 | Instruqt Track update | 2025-02-24 | 2025-03-07 | 2 | Monica Miller | Not Started | Not Started
CDL - Workshop | Auto Renewed Certs |  | Workshop run through |  |  | 1 |  | Not Started | Not Started | Run through workshop end to end - deck/track (updated) to identify any additional gaps in the story/track
CDL - Demo | Auto Renewed Certs |  | Demo (Build) | 2025-01-22 | 2025-02-14 | 5 | Guilherme Pamplona Santos | Development | Under Review | Readme in progress. Demo requires SE review (run through) post SKO.
CDL - Demo | Auto Renewed Certs |  | DDR Demo Review (SE's) | 2025-02-14 | 2025-02-28 | 3 | Rama Chavali | Development | On Track | SE testing and feedback on DDR Demo and Readme. Rama will do, add further SE's post SKO
CDL - Demo Recording | Auto Renewed Certs |  | Demo recording for 2nd call Deck | 2025-02-24 | 2025-02-28 | 1 |  | Not Started | Not Started | Is this just a bite size demo to whet the appetite for the full DDR Demo?
CDL - Demo Context Slides | Auto Renewed Certs |  | Customer Facing Context Slides | 2025-02-24 | 2025-02-28 | 1 |  | Not Started | Not Started | Context slides to oriente the customer if the Demo is used on its own/not show within the context of the 2nd call deck
Discovery Guide | Auto Renewed Certs |  | Discovery Guide (Build) | 2025-01-17 | 2025-02-07 | 5 | Justin DeFrank Nico Kabar | Development | Under Review | Feedback underway
Objection Handling Guide | Auto Renewed Certs |  | Objection Handing Guide (Build) | 2025-01-17 | 2025-02-07 | 5 | David Howes Nico Kabar | Development | Under Review | Feedback underway
Handoff | Auto Renewed Certs |  | Handoff for publishing (Highspot / Playbooks) | 2025-03-07 | 2025-03-07 | 1 | Fiona Black | Not Started | Not Started
Feedback | Auto Renewed Certs |  | TFO, BVS, Sales feedback | 2025-02-24 | 2025-03-05 | 3 |  | Not Started | Not Started
Design Work | Auto Renewed Certs |  | Content to Creative Design for polishing | 2025-03-10 | 2025-03-14 | 5 | Fiona Black | Not Started | Not Started
Publish | Auto Renewed Certs |  | Publish (Prep) | 2025-03-17 | 2025-03-18 | 2 | Cailin Kearns Claudia Lannes | Not Started | Not Started
Publish | Auto Renewed Certs |  | Publish (Highspot) | 2025-03-18 | 2025-03-18 | 1 | Cailin Kearns | Not Started | Not Started
Publish | Auto Renewed Certs |  | Publish (Playbooks) | 2025-03-18 | 2025-03-21 | 3 | Claudia Lannes | Not Started | Not Started
Enablement | SKO Session |  | Recording: Introduction to Technical Play Framework | 2025-01-22 | 2025-01-28 | 1 | Adam Cavaliere | Published | Published | Prework for SKO session; re-use this deck content https://docs.google.com/presentation/d/1gnFWDtUNGjunybxEwHPDcCAS0rVZ0R3yK6GHlsPB0AM/edit?pli=1#slide=id.g31dfbc5894d_0_1
Enablement | SKO Session |  | Recording: Re-introduce Maturity Quadrant, focusing on the WHY | 2025-01-22 | 2025-01-28 | 1 | Corrigan Neralich | Published | Published
Feedback Loop | Technical Plays |  | Build formal feedback process | 2025-03-05 | 2025-03-12 | 3 | Fiona Black | Not Started | Not Started

## Risk Log
Date | Date Closed | Reporter Name | Identification (Asset Name, Resource Name, etc.) | Reported Health | Description | Category | Requested Action | Status
2025-01-17 | 2025-01-27 | Fiona Black | Certs Workshop Build | Potential Risk | No SE with available cycles | Resource | Contacted Chris Roberson to ask for additional resource. Will need to get resource up to speed ASAP | Closed | Rama Chavali assigned, added Mahil El Khatib 01/30
2025-01-18 | 2025-01-22 | Fiona Black | Certs Demo Build | Potential Risk | No SE with available cycles | Resource | Contacted Chris Roberson to ask for additional resource. Will need to get resource up to speed ASAP | Closed | Guilherme Pamplona Santos assigned

## Change Log
Change Number | Date | Requested By | Reason for Change | Reason for Change | Jira Ticket | Description | Status | Actions Related to the Change